## Slide 1: Community Service Centre Project
Action Plan, Progress Report, Questionnaire & Lessons Learned
Presented by: Mncwabe Nonjabulo
Date: 20/09/2024

## Slide 2: Action Plan Overview
The purpose of the action plan is to monitor goals and objectives of the Community Service Center.
Focus on delivering essential services like health check-ups, literacy programs, and vocational training.
Collaboration with stakeholders such as community leaders, volunteers, and NGOs.

## Slide 3: Key Activities in the Action Plan
Identifying Community Needs: Surveys, interviews, and focus groups to understand the community’s challenges.
Developing Service Programs: Tailored services like health check-ups, after-school tutoring, and vocational training.
Monitoring and Adjusting Programs: Regular evaluation and feedback collection to ensure service effectiveness.

## Slide 4: Roles & Responsibilities
Team Lead: Oversees project activities and ensures alignment with community needs.
Volunteers: Assist in delivering services and gathering feedback from participants.
Stakeholders: Provide guidance, resources, and support for program execution.

## Slide 5: Progress Report
Summary of the project’s execution phase.
Focus on the achievements to date, activities completed, and outstanding tasks.

## Slide 6: Completed Activities
Community Needs Assessment completed with over 200 participants.
Health Check-up and Literacy programs launched.
Volunteers trained and assigned to specific service areas.

## Slide 7: Outstanding Activities
Ongoing Monitoring: Weekly tracking of program success and participation.
Program Feedback Collection: Gathering input from community members to refine services.
Final Evaluation of Execution Phase: Preparing a comprehensive report on the project's progress.

## Slide 8: Stakeholder Questionnaire
The questionnaire is designed to gather feedback from stakeholders about the Community Service Center’s programs.
Focus on the effectiveness of services, areas for improvement, and future needs.

## Slide 9: Sample Questions
Open-Ended Questions:
What are the key needs the project should address?
How effective has the project been so far?
Suggestions for improvements?
Closed-Ended Questions:
Are you satisfied with the current services? (1-5 scale)
Are the programs aligned with the community’s needs? (Yes/No/Unsure)

## Slide 10: Lessons Learned & Key Lessons Learned
Reflect on key takeaways from the project execution.
Areas covered: Initiation and planning, monitoring, quality management, leadership, teamwork.
  Planning: Scope should be narrow and focused from the start.
  Monitoring: Real-time reporting and regular reviews are crucial for adapting quickly.
  Quality Management: Community feedback was key to improving services.
  Leadership: Collaborative leadership helped engage volunteers and stakeholders.
  Teamwork: Clear communication and teamwork were critical for project success.